## project WBS monitor
project: | WorkBreakdown Structure (WBS) monitor |  |  | remark | WBS id is reference to chapter in functional design (FD)
ScenarioCreator, beveiliging |  |  |  | remark | for FD: chapter are not chronological
date: | 2018-10-09 |  |  | do not | change the WBS id number for a task
WBS id | predecessor | task | requirement level (MoSCoW) | developer | Risc | duration, hr (plan) | duration, hr (do) | evaluation (check) | action (act)
1 |  | Loginfunctie | MUST | Dylan + Ryan |  |  | 4
2 |  | Loginfunctie encryptie | Should | Dylan + Ryan |  |  | 4
3 |  | Plattegrond met Grid | MUST | Dylan + Ryan |  |  | 4.5
4 |  | Navigatie van tabjes dynamisch gemaakt | MUST | Ryan |  |  | 2
5 |  | Flash messages geoptimaliseerd | MUST | Dylan |  |  | 4.5
6 |  | Gebruiker toevoegen | MUST | Ryan |  |  | 1.5
7 |  | Gebruiker wijzigen | MUST | Ryan |  |  | 2
8 |  | Nieuw scenario toevoegen | MUST | Dylan |  |  | 4
9 |  | Scenario activeren (met of zonder hulpmiddelen) | MUST | Dylan |  |  | 2
10 |  | Dynamisch geluid inladen | MUST | Dylan + Ryan |  |  | 2
11 |  | Scenarios wijzigen | MUST | Ryan |  |  | 3
12 |  | Scenario afronden en confirmation laten zien | MUST | Dylan |  |  | 2
13 |  | Alarm laten zien op student accounts | MUST | Dylan |  |  | 1
14 |  | Cleaned up HTML CSS | MUST | Maarten |  |  | 8
15 |  | Installatie bij beveiliging | MUST | Dylan + Ryan + Maarten |  |  | 2.5
16 |  | Update: geluid toevoegen | MUST | Dylan + Ryan |  |  | 1.5
17 |  | Update: Gebruikersrechten gewisseld | MUST | Dylan + Ryan |  |  | 1.5
18
19
|  | total |  |  |  | 0 | 50
Maarten 10, Ryan en Dylan 20

## MoSCoW
M | MUST | Describes a requirement that must be satisfied in the final solution for the solution to be considered a success.
S | SHOULD | Represents a high-priority item that should be included in the solution if it is possible. This is often a critical requirement but one which can be satisfied in other ways if strictly necessary.
C | COULD | Describes a requirement which is considered desirable but not necessary. This will be included if time and resources permit.
W | WON'T | Represents a requirement that stakeholders have agreed will not be implemented in a given release, but may be considered for the future. (note: occasionally the word "Would" is substituted for "Won't" to give a clearer understanding of this choice).

## version
datum | door | versieomschrijving
2015-10-09 | kadi | originele basisversie aangepast aan ideeën van Six Sigma